## TaskList
Task List Report - Preview / Review
Team No. |  | 3 |  | Est. | Act. | Supervisor | Mr. Alex Toh
Team Member |  | Eugene | M1 | 5 | 0 | From | 2017-02-13
|  | Yoong Soon | M2 | 3 | 0 | To | 2017-02-17
|  | Ming Xiu | M3 | 0 | 0 | Preview | 2017-02-13
|  | Beckham | M4 | 0 | 0 | Review | 2017-02-17
Preview | [7 empty] | Description of Task | Review
No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
1 | Creating a sphere for projectile |  | M2 | 1 |  |  |  |  | M2 | 1
2 | Making the sphere appear with keypress |  | M2 | 1 |  |  |  |  | M2 | 1
3 | Moving the sphere forward after keypress |  | M2 | 1 |  |  |  |  | M2 | 1
4 | Detecting if camera next position is an object |  | M1 | 2 |  |  |  |  | M1 | 2
5 | Preventing camera from moving if next position is an object |  | M1 | 1 |  |  |  |  | M1 | 1
6 | Pressing spacebar increases position y |  | M1 | 1 |  |  |  |  | M1 | 1
7 | Automatically decrease position y to 0 when position y > 0 |  | M1 | 1 |  |  |  |  | M1 | 1
8
Total |  |  |  | 8 | [5 empty] | 8
Comments for preview | [8 empty] | Comments for review
(Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
Eugene |  |  |  | Yoong Soon |  |  |  |  | Eugene |  |  | Yoong Soon
Ming Xiu |  |  |  | Beckham |  |  |  |  | Ming Xiu |  |  | Beckham
Note on F10: HONG CHRIS: Estimated volume of the task
Note on M10: HONG CHRIS: Actual volume after work done