## TaskList
Task List Report - Preview / Review
| Team No. |  | 3 |  | Est. | Act. | Supervisor | Mr. Alex Toh
| Team Member |  | Eugene | M1 | 40 | 0 | From | 2017-02-13
|  |  | Yoong Soon | M2 | 40 | 0 | To | 2017-02-17 |  | x
|  |  | Ming Xiu | M3 | 40 | 0 | Preview | 2017-02-13
|  |  | Beckham | M4 | 40 | 0 | Review | 2017-02-17
| Preview | [7 empty] | Description of Task | Review
| No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
| 1 | Creating a sphere for projectile |  | M2 | 1 |  |  |  |  | M2 | 1
| 2 | Making the sphere appear with keypress |  | M2 | 1 |  |  |  |  | M2 | 1
| 3 | Moving the sphere forward after keypress |  | M2 | 1 |  |  |  |  | M2 | 1
| 4 | Detecting if camera next position is an object |  | M1 | 1 |  |  |  |  | M1 | 1
| 5 | Preventing camera from moving if next position is an object |  | M1 | 1 |  |  |  |  | M1 | 1
| 6 | Pressing spacebar increases position y |  | M1 | 1 |  |  |  |  | M1 | 1
| 7 | Automatically decrease position y to 0 when position y > 0 |  | M1 | 1 |  |  |  |  | M1 | 1
| 8 | Skybox |  | M1 | 1 |  |  |  |  | M1 | 1
| 9 | NPC Model |  | M3 | 8 |  |  |  |  | M3 | 8
| 10 | Lava platform model |  | M2 | 1 |  |  |  |  | M2 | 1
| 11 | Deal damage when stepped on lava |  | M2 | 1 |  |  |  |  | M2 | 1
| 12 | Speed battery model |  | M1 | 1 |  |  |  |  | M1 | 1
| 13 | Increase speed when speed battery is taken |  | M1 | 1 |  |  |  |  | M1 | 1
| 14 | Enemy pathfinding |  | M2 | 4 |  |  |  |  | M2 | 4
| 15 | Enemy range detection; if player is near |  | M2 | 2 |  |  |  |  | M2 | 2
| 16 | Enemy object |  | M4 | 4 |  |  |  |  | M4 | 4
| 17 | Deplete enemy health when hitted |  | M4 | 1 |  |  |  |  | M4 | 1
| 18 | Spawn bullet when keypressed |  | M3 | 1 |  |  |  |  | M3 | 1
| 19 | Translating bullet |  | M1 | 1 |  |  |  |  | M1 | 1
| 20 | Delete bullet after defined range |  | M1 | 1 |  |  |  |  | M1 | 1
| 21 | Bullet direction based on target |  | M2 | 1 |  |  |  |  | M2 | 1
| 22 | FPS Camera |  | M1 | 4 |  |  |  |  | M1 | 4
| 23 | WASD Movement |  | M1 | 1 |  |  |  |  | M1 | 1
| 24 | Equipping weapon; bind to character |  | M4 | 4 |  |  |  |  | M4 | 4
| 25 | Collision detection |  | M1 | 4 |  |  |  |  | M1 | 4
| 26 | Bound check |  | M1 | 1 |  |  |  |  | M1 | 1
| 27 | Inventory Interface |  | M4 | 4 |  |  |  |  | M4 | 4
| 28 | Displaying weapon/item icon on inventory |  | M4 | 2 |  |  |  |  | M4 | 2
| 29 | Tutorial Level; design, placing objects and enemies |  | M1 | 2 |  |  |  |  | M1 | 2
| 30 | Level 1; design, placing objects and enemies |  | M3 | 8 |  |  |  |  | M3 | 8
i | 31 | Level 2; design, placing objects and enemies |  | M2 | 8 |  |  |  |  | M2 | 8
| 32 | Level 3; design, placing objects and enemies |  | M4 | 8 |  |  |  |  | M4 | 8
| 33 | Level 4; design, placing objects and enemies |  | M1 | 8 |  |  |  |  | M1 | 8
| 34 | Bonus/Boss Level; design, placing objects and enemies |  | M1 | 8 |  |  |  |  | M1 | 8
| 35 | Bonus/Boss Level; design, placing objects and enemies |  | M2 | 8 |  |  |  |  | M2 | 8
| 36 | Bonus/Boss Level; design, placing objects and enemies |  | M3 | 8 |  |  |  |  | M3 | 8
| 37 | Bonus/Boss Level; design, placing objects and enemies |  | M4 | 8 |  |  |  |  | M4 | 8
| 38 | Importing models |  | M3 | 4 |  |  |  |  | M3 | 4
| 39 | Hierarchical modelling |  | M3 | 4 |  |  |  |  | M3 | 4
| 40 | Designing torchlight model |  | M3 | 2 |  |  |  |  | M3 | 2
| 41 | Designing sword model |  | M3 | 2 |  |  |  |  | M3 | 2
| 42 | Designing fist model |  | M3 | 1 |  |  |  |  | M3 | 1
| 43 | Designing gun model |  | M3 | 2 |  |  |  |  | M3 | 2
| 44 | Creating enemy class |  | M2 | 8 |  |  |  |  | M2 | 8
i | 45 | Designing splash screen |  | M1 | 1 |  |  |  |  | M1 | 1
i | 46 | Designing main menu |  | M1 | 2 |  |  |  |  | M1 | 2
| 47 | Designing pause menu; press esc to continue, back return to menu and quit. |  | M2 | 4 |  |  |  |  | M2 | 4
| 48 | Minimap interfance |  | M4 | 4 |  |  |  |  | M4 | 4
| 49 | Object moving on minimap |  | M4 | 4 |  |  |  |  | M4 | 4
| 50 | Health counter |  | M4 | 1 |  |  |  |  | M4 | 1
51
52
53
54
55
56
| Total |  |  |  | 147 | [5 empty] | 147
| Comments for preview | [8 empty] | Comments for review
| (Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
| Eugene |  |  |  | Yoong Soon |  |  |  |  | Eugene |  |  | Yoong Soon
| Ming Xiu |  |  |  | Beckham |  |  |  |  | Ming Xiu |  |  | Beckham
Note on F10: HONG CHRIS: Estimated volume of the task
Note on M10: HONG CHRIS: Actual volume after work done